## Quiz night example
Event run sheet: quiz night example
Change the start time and every time below moves with it. Minutes are counted from doors open.
Doors open | 19:00
Time | Minutes from doors | What happens | Who | Notes | Done
| -120 | Venue access. Set out tables, team numbers, answer sheets and pens. | Set-up crew (3) | Test the microphone and projector now, not at 6.55.
| -60 | Raffle and auction tables set up. Float counted by two people. | Treasurer and raffle seller | Write the float total on the cash box lid.
| -30 | Volunteers briefed. Quizmaster sound check. | Organiser | Everyone knows where the first aid kit and fire exits are.
| 0 | Doors open. Teams sign in and pay or show their booking. | Door and greeter | Card reader charged. Tick teams off the booking list.
| 30 | Welcome, housekeeping and thanks to sponsors. | Quizmaster | Toilets, fire exits, bar, what the night is raising for.
| 35 | Round 1 | Quizmaster; runners collect sheets
| 50 | Round 2 | Quizmaster; markers start scoring
| 65 | Round 3, then scores on the board | Quizmaster and scorers
| 80 | Break: supper, raffle tickets on sale, silent auction open. | Raffle sellers and kitchen | Announce the running total to keep energy up.
| 100 | Round 4 | Quizmaster
| 115 | Round 5 | Quizmaster
| 130 | Silent auction closes. Live auction (three lots). | Auctioneer and bid-table monitor | Close the silent auction on time, by the clock.
| 145 | Round 6 (final round) | Quizmaster
| 160 | Raffle draw from sold tickets, with an independent witness. | Drawer and witness | Read out the winning numbers twice.
| 170 | Final scores, winners, booby prize, thank-yous and the total so far. | Quizmaster
| 180 | Pay-up and collection for auction items. Pack down. | Checkout and everyone left | No item leaves until it is paid for.
| 210 | Takings counted in pairs and sealed. | Treasurer and one other | Bank the next working day.
From the free fundraising guide by For Goods Sake. General information, not financial or legal advice.

## Blank run sheet
Event run sheet
Time, what happens, who is responsible, and anything they need to know.
Event |  |  | Date
Time | What happens | Who | Notes | Done